## Cricket
S.No | Task | SubTask | Completion Dates
1 | Cricket Pitch | Cricket pitch measurements | 4thJune
2 |  | Type of Cricket pitches
3 |  | Turf Pitch cricket
4 |  | Roof top pitch circket
5 |  | box pitch circket
6 | Pitch Design | 26sqrt*57sqrt Total area
7 |  | box pitch design
8 |  | Floor sand
9 |  | Floor material
10 |  | Floor gross
11 |  | Floor cleanups equipments
12 | Fencing Design | Types of polls
13 |  | No.of polls | 5th June
14 |  | position of polls
15 |  | Types of nets
16 |  | No.of nets
17 |  | Position of nets
18 |  | length of nets
19 |  | Top roof for rain season
20 |  | cover items
21 |  | Types of items
22 |  | Covering type (flexible open and close)
23 | Surronding water flow | Type of fixes
24 |  | water flow for surronding
25 |  | Rain water flush
26 | Lighting for Night | Types of lights
27 |  | No.of lights | 6th June
28 |  | position of lights
29 |  | focus of lights
30 | Play Ground Matt | Types of Matt
31 |  | Tenis ball support
32 |  | Rubber ball support
33 |  | kark ball support
34 |  | Kutulaball support
35 | Sitting Area | Types of sitting ways
36 |  | Types of resting area | 7th June
37 |  | Types of Chairs
38 |  | Types of Tables
39 |  | Types of equipments
40 |  | Area for sitting
41 | Washroom Design | Total Area
42 |  | Types of design
43 |  | Measurements
44 |  | washing equipment
45 | Cafeteria Design | Total Area
46 |  | Types of design
47 |  | Measurements
48 |  | Relaxing equipment
49

## Shuttle
S.No | Task | SubTask | Completion Dates
1 | Shuttle Pitch | Shuttle pitch measurements | 4thJune
2 |  | Type of Shuttle pitches
3 |  | single play shuttle court
4 |  | double play shuttle court
5 |  | mixed play shuttle court
6 | Pitch Design | 26t*50sqrt Total area
7 |  | double play shuttle court
8 |  | Floor sand
9 |  | Floor material
10 |  | Floor gross
Floor markers
11 |  | Floor cleanups equipments
12 | Fencing Design | Types of polls | 5th June
13 |  | No.of polls
14 |  | position of polls
15 |  | Types of nets
16 |  | No.of nets
17 |  | Position of nets
18 |  | length of nets
19 |  | Top roof for rain season
20 |  | cover items
21 |  | Types of items
22 |  | Covering type (flexible open and close)
23 | Surronding water flow | Type of fixes
24 |  | water flow for surronding
25 |  | Rain water flush
26 | Lighting for Night | Types of lights | 6th June
27 |  | No.of lights
28 |  | position of lights
29 |  | focus of lights
30 | Play Ground Matt | Types of Matt
31 |  | Matt Arrangements
32 |  | Matt Design
33 |  | Matt Measurement
34 |  | Matt colors
35 | Sitting Area | Types of sitting ways | 7th June
36 |  | Types of resting area
37 |  | Types of Chairs
38 |  | Types of Tables
39 |  | Types of equipments
40 |  | Area for sitting
41 | Washroom Design | Total Area
42 |  | Types of design
43 |  | Measurements
44 |  | washing equipment
45 | Cafeteria Design | Total Area
46 |  | Types of design
47 |  | Measurements
48 |  | Relaxing equipment

## Volleyball
S.No | Task | SubTask | Completion Dates
1 | Volleyball Pitch | Volleyball court measurements | 4thJune
2 |  | Type of Volleyball courts
3 |  | single play court
4 |  | double play court
5 |  | mixed play court
6 | Court Design | 26t*50sqrt Total area
7 |  | double play shuttle court
8 |  | Floor sand
9 |  | Floor material
10 |  | Floor gross
Floor markers
11 |  | Floor cleanups equipments
12 | Fencing Design | Types of polls | 5th June
13 |  | No.of polls
14 |  | position of polls
15 |  | Types of nets
16 |  | No.of nets
17 |  | Position of nets
18 |  | length of nets
19 |  | Top roof for rain season
20 |  | cover items
21 |  | Types of items
22 |  | Covering type (flexible open and close)
23 | Surronding water flow | Type of fixes
24 |  | water flow for surronding
25 |  | Rain water flush
26 | Lighting for Night | Types of lights | 6th June
27 |  | No.of lights
28 |  | position of lights
29 |  | focus of lights
30 | Play Ground Matt | Types of Matt
31 |  | Matt Arrangements
32 |  | Matt Design
33 |  | Matt Measurement
34 |  | Matt colors
35 | Sitting Area | Types of sitting ways | 7th June
36 |  | Types of resting area
37 |  | Types of Chairs
38 |  | Types of Tables
39 |  | Types of equipments
40 |  | Area for sitting
41 | Washroom Design | Total Area
42 |  | Types of design
43 |  | Measurements
44 |  | washing equipment
45 | Cafeteria Design | Total Area
46 |  | Types of design
47 |  | Measurements
48 |  | Relaxing equipment

## Tennikoit
S.No | Task | SubTask | Completion Dates
1 | Tennikoit Court | Tennikoit court measurements | 4thJune
2 |  | Type of tennikoit courts
3 |  | single play court
4 |  | double play court
5 |  | mixed play court
6 | Court Design | 26t*50sqrt Total area
7 |  | double play shuttle court
8 |  | Floor sand
9 |  | Floor material
10 |  | Floor gross
Floor markers
11 |  | Floor cleanups equipments
12 | Fencing Design | Types of polls | 5th June
13 |  | No.of polls
14 |  | position of polls
15 |  | Types of nets
16 |  | No.of nets
17 |  | Position of nets
18 |  | length of nets
19 |  | Top roof for rain season
20 |  | cover items
21 |  | Types of items
22 |  | Covering type (flexible open and close)
23 | Surronding water flow | Type of fixes
24 |  | water flow for surronding
25 |  | Rain water flush
26 | Lighting for Night | Types of lights | 6th June
27 |  | No.of lights
28 |  | position of lights
29 |  | focus of lights
30 | Play Ground Matt | Types of Matt
31 |  | Matt Arrangements
32 |  | Matt Design
33 |  | Matt Measurement
34 |  | Matt colors
35 | Sitting Area | Types of sitting ways | 7th June
36 |  | Types of resting area
37 |  | Types of Chairs
38 |  | Types of Tables
39 |  | Types of equipments
40 |  | Area for sitting
41 | Washroom Design | Total Area
42 |  | Types of design
43 |  | Measurements
44 |  | washing equipment
45 | Cafeteria Design | Total Area
46 |  | Types of design
47 |  | Measurements
48 |  | Relaxing equipment

## TaskList
S.No | Project | TeamLead | Team_Members
1 | Cricket Pitch Arrangement | Santhosh | Swathi
2 | Shuttle Court Arrangement | Naga Durga | Prasana
3 | VolleyBall Court Arrangement | Jayasri | Bujji
4 | Tennikoit Court Arrangement | Nasheena | Mahabunissa